## Sheet 1
BdN Procurement Opportunities
|  |  |  | EOI Close Date | Proponents List | RFP Issue Date | Forecasted Contract Award Date
| Contract | Description | Status |  |  |  |  | Awarded Supplier
Subsea, Umbilicals, Risers, and Flowlines (SURF)
| Geotechnical Offshore Soil Investigation | A site-specific geotechnical program including mobilization of vessel, equipment and approraite survey location, transit to survey location, positioning calibrations and sea trials, pre-drilling ROV video survey on certain locations, testing and sampling at approximately 30 locations, transit to demobilization port and demobilization of vessel, equipment and personnel, and onshore labratory testing of samples and final reporting | Awarded | 2018-10-12 |  | 2018-11-14 | 2018-12-21 | Fugro GeoSurveys Inc.
| SURF Concept Studies | Subsea and Marine (SURF EPCI) Concept Study for the Bay du Nord Development Project. Equinor was seeking SURF EPCI partnerships (Alliance or Subcontractor) that can perform an integrated SPS and marine scope of work of this magnitude considering the harsh environment and unique conditions offshore NL | Awarded | 2018-10-19 |  | 2018-11-07 | 2018-11-26 | SIA (Subsea 7 Canada & OneSubsea) Technip FMC Canada Ltd. (TFMC)
| SURF FEED and optional iECPI* | SURF iEPCI Contract consisting of FEED with option for Execution and Aftermarket | In Progress | N/A | SIA (Subsea 7 Canada & OneSubsea) Technip FMC Canada Ltd. (TFMC) | November 2019 | FEED: TBD EPCI: TBD
Floating Production Storage and Offloading (FPSO)
| FPSO Topsides concept study |  | Awarded | 2018-10-19 |  |  |  | WorleyParsons/TechnipFMC/Hatch Kiewit/Wood Aker/Kvaerner
| FPSO Pre-FEED study |  | Awarded | N/A |  |  |  | Kiewit/Wood Aker/Kvaerner
| Hull yard familiarisation study |  | Awarded | N/A |  |  |  | Daewoo Shipbuilding & Marine Engineering (DSME) Samsung Heavy Industries (SHI) Sembcorp
| Turret concept study |  | Awarded | N/A |  |  |  | SBM Offshore Services APL Norway AS
| BdN Hull design contract |  | Awarded | N/A |  |  |  | Salt Ship Design AS
| Safety Automation System (SAS) - Pre-FEED integration Study |  | Awarded | 2019-01-19 |  |  |  | ABB AS Honeywell AS Kongsberg Maritime
| Classification Society and Certifying Authority | The roles of Certifying Authority (CA) and Classifications Society (CS) for a newbuild Floating Production Storage and Offloading Project (Bay du Nord) | Awarded | 2019-03-25 |  | 2019-05-01 | 2019-08-06 | Det Norske Veritas (Canada) Ltd. (DNV)
| Turret Mooring System FEED&optional EPC contract | All engineering, procurement, fabrication, transportation and integration/installation assistance for the TMS system, with exception suction anchor fabrication and installation of buoy at field. FEED and Option for Execution of the Turret Mooring System | In Progress | N/A | SBM Offshore Services APL Norway AS | 2019-08-28 | FEED: TBD EPC: TBD
| FPSO FEED&optional EPC contract - Hull and Topside* | All engineering, procurement, fabrication, integration and commissioning of the Hull and the Topside | In Progress | N/A | Kiewit/Wood Kvaerner/Aker | November 2019 | FEED: TBD EPC: TBD
| Safety Automation System (SAS) contract | Safety and Automation Systems (SAS) Project Specific Agreement (PSA) for the Green Field (GF) phase and for the Operation, Modification, Maintenance and Upgrade (OMMU) phase. The GF phase will cover deliveries for topside, hull, turret, subsea and an onshore control room | In Progress | 2019-06-01 | ABB Emmerson Process Management Kongsberg Maritime Siemens | 2019-09-01 | TBD
* EOI for concept study included the FEED and EPC phase